

< Project Title >

Process Report

Version ??.??

**Start Date: ?? /?? /????**

**Authors : Student1, s1234567**

**Student2, s1234567**

**Student3, s1234567**

**Student4, s1234567**

**Student5, s1234567**

**Student6, s1234567**

Document Control

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Version #** | **Implemented** | **Implementation** | **Reviewed** | **Approval** | **Reason** |
| **By** | **Date** | **By** | **Date** |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

**STAFF or ENTITIES CONSULTED**

|  |  |
| --- | --- |
| **Name** | **Position / Organization** |
| Maria Spichkova | Lecturer-IF, RMIT University |

TABLE OF CONTENTS

1 Executuve Summary 4

2 Project Team 4

3 Methodology 4

4 Project Management tools 4

5 Project Workflow 4

# 

# 

# Executuve Summary

Write here the executive summary of the project of the project (200-300 words).

—Overview and project aim

This project includes the design and constructions of the Menti -- an exclusive website which allows mentoring become more efficient by using non face-to-face way. The primary aim of this was to design and construct such a website which members can successfully contact between mentor and mentee and do mentoring.

—Outline of Process and Planning stage

Initially, we separate our team into two teams -- front-end and backend. Fount-end referred to design the straight version of our website and the backend is to add the function of payment and store the database.

—Outline the evolution

The project has a good flow to assist the user to register and start communicating whether with mentis or mentors. The project flow is user friendly due to numbers of functional requirements that make the user using of the system simple and helpful. For example, mentis can search for their preferable mentor and communicate with mentor. Also, mentis can make payment while communicating with mentor and accept mentor rates. On the other hand, notification function alert mentor of a new menti needs tutoring, then they can communicate through private messages in the messaging page. Mentis can rate mentors depends on their own experiments with them, and other mentis are able to view the mentor rate before communicating him.

# Project Team

* Saransh: Working on the frontend, designing Menti pages. Coding in HAML and CSS.
* Amandeep: Working on the frontend, designing Menti pages. Coding in HAML and CSS.
* Rittidate: Working on the backend, design Menti database and implement functions. Coding in Ruby on Rails.
* Ahmed: Working on the backend, design Menti database and implement functions. Coding in Ruby on Rails, and document the project.
* Qiuwen: Working on the backend, design Menti database and implement functions. Coding in Ruby on Rails, and document the project.

# Methodology

Agile methodology is the methodology applied in Menti project. Agile is a methodology for producing software products efficiently and quickly. It accumulates a group of techniques in order to make the development iterative. Moreover, it involves customer in all development phases which makes it more adaptive and responsive method. Some of Agile Features:

1- Agile has a higher priority to satisfy customer requirements.

2- Changes are not an issue, even after a while of developing.

3- Progress delivery can be done weekly, till finish the project.

4- Encourage face to face meetings with clients and team members.

In Menti project the group used sprints to determine their progress weekly. A sprint is a development iteration. Sprints are intended to be weekly work iterations. Everyone in the team fill the sprint weekly to determine the team member progress before meeting the client. Work Break down Structure (WBS) has been used in Menti as a key project deliverable to organize the team work with in manageable sections. Menti WBS below:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ID | Task Name | Duration | Start\_Date | Finish\_Date | Resource\_Names | Hours\_Sum |
| 1 | Sprint 1 (Week 4) | 6 days | August 5, 2016 8:00 AM | August 12, 2016 5:00 PM |  |  |
| 1.1 | Framework setup | 6 hrs | August 9, 2016 8:00 AM | August 9, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 1.2 | Backend setup | 10 hrs | August 10, 2016 8:00 AM | August 11, 2016 10:00 AM | Rittidate Kittisarathamma |  |
| 1.3 | Team meeting(1) | 2 hrs | August 8, 2016 8:00 AM | August 8, 2016 10:00 AM | Rittidate Kittisarathamma |  |
| 1.4 | Login page backend | 6 hrs | August 11, 2016 8:00 AM | August 11, 2016 3:00 PM | Rittidate Kittisarathamma | 24 |
| 1.5 | Team meeting(1) | 30 mins | August 4, 2016 8:00 AM | August 4, 2016 8:30 AM | Saransh Sandeepbhai Seth |  |
| 1.6 | Installation of framework on windows | 6 hrs | August 6, 2016 8:00 AM | August 6, 2016 3:00 PM | Saransh Sandeepbhai Seth |  |
| 1.7 | Login and registration page design | 3 hrs | August 9, 2016 8:00 AM | August 9, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 1.8 | Team meeting(2) | 2 hrs | August 8, 2016 8:00 AM | August 8, 2016 10:00 AM | Saransh Sandeepbhai Seth | 11.5 |
| 1.9 | Team meeting(1) | 30 mins | August 4, 2016 8:00 AM | August 4, 2016 8:30 AM | Amandeep Nagi |  |
| 1.10 | Installiation of the  framework(It had problem with windows) | 7 hrs | August 6, 2016 8:00 AM | August 6, 2016 4:00 PM | Amandeep Nagi |  |
| 1.11 | Documentation attlasien+trello | 2 hrs | August 7, 2016 8:00 AM | August 7, 2016 10:00 AM | Amandeep Nagi |  |
| 1.12 | Team meeting(2) | 2 hrs | August 8, 2016 8:00 AM | August 8, 2016 10:00 AM | Amandeep Nagi | 11.5 |
| 1.13 | Team meeting(1) | 30 mins | August 4, 2016 8:00 AM | August 4, 2016 8:30 AM | Qiuwen Yao |  |
| 1.14 | Installations of framework | 7 hrs | August 6, 2016 8:00 AM | August 6, 2016 4:00 PM | Qiuwen Yao |  |
| 1.15 | Mock ups of the login page | 2.5 hrs | August 11, 2016 8:00 AM | August 11, 2016 10:30 AM | Qiuwen Yao |  |
| 1.16 | Team meeting(2) | 2 hrs | August 8, 2016 8:00 AM | August 8, 2016 10:00 AM | Qiuwen Yao |  |
| 1.17 | learn about Ruby by video | 8 hrs | August 7, 2016 8:00 AM | August 7, 2016 5:00 PM | Qiuwen Yao |  |
| 1.18 | Team meeting(1) | 30 mins | August 4, 2016 8:00 AM | August 4, 2016 8:30 AM | Qiuwen Yao |  |
| 1.19 | Installation of framework | 6.5 hrs | August 5, 2016 8:00 AM | August 5, 2016 3:30 PM | Qiuwen Yao |  |
| 1.20 | Team meeting(2) | 2 hrs | August 8, 2016 8:00 AM | August 8, 2016 10:00 AM | Qiuwen Yao | 28.5 |
| 1.21 | Team meeting 1 | 30 mins | August 4, 2016 8:00 AM | August 4, 2016 8:30 AM | Ahmed Fahad Alajmi |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1.22 | Installation of framework windows | 6 hrs | August 6, 2016 8:00 AM | August 6, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 1.23 | Team meeting 2 | 2 hrs | August 8, 2016 8:00 AM | August 8, 2016 10:00 AM | Ahmed Fahad Alajmi | 8.5 |
| 2 | Sprint 2 (week 5) | 6 days | August 12, 2016 8:00 AM | August 19, 2016 5:00 PM |  |  |
| 2.1 | Team Meeting | 2 hrs | August 15, 2016 8:00 AM | August 15, 2016 10:00 AM | Rittidate Kittisarathamma |  |
| 2.2 | Research library needed | 3 hrs | August 15, 2016 8:00 AM | August 15, 2016 11:00 AM | Rittidate Kittisarathamma |  |
| 2.3 | Clearify workflow | 6 hrs | August 16, 2016 8:00 AM | August 16, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 2.4 | Database schema design | 6 hrs | August 17, 2016 8:00 AM | August 17, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 2.5 | Merge design | 5 hrs | August 19, 2016 8:00 AM | August 19, 2016 2:00 PM | Rittidate Kittisarathamma | 22 |
| 2.6 | Team Meeting | 2 hrs | August 15, 2016 8:00 AM | August 15, 2016 10:00 AM | Saransh Sandeepbhai Seth |  |
| 2.7 | Understanding the Project structure for Ruby | 5 hrs | August 15, 2016 8:00 AM | August 15, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 2.8 | Redesigning Pages | 5 hrs | August 17, 2016 8:00 AM | August 17, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 2.9 | Redesigning Pages | 6 hrs | August 18, 2016 8:00 AM | August 18, 2016 3:00 PM | Saransh Sandeepbhai Seth |  |
| 2.10 | Redesigning Pages and merge code | 4 hrs | August 19, 2016 8:00 AM | August 19, 2016 12:00 PM | Saransh Sandeepbhai Seth | 22 |
| 2.11 | Team Meeting | 2 hrs | August 15, 2016 8:00 AM | August 15, 2016 10:00 AM | Amandeep Nagi |  |
| 2.12 | Understanding the Project structure for Ruby | 6 hrs | August 15, 2016 8:00 AM | August 15, 2016 3:00 PM | Amandeep Nagi |  |
| 2.13 | Understanding front-end stuff for Ruby | 5 hrs | August 17, 2016 8:00 AM | August 17, 2016 2:00 PM | Amandeep Nagi |  |
| 2.14 | Redesigning Pages | 4 hrs | August 18, 2016 8:00 AM | August 18, 2016 12:00 PM | Amandeep Nagi |  |
| 2.15 | Redesigning Pages and merge code | 4 hrs | August 19, 2016 8:00 AM | August 19, 2016 12:00 PM | Amandeep Nagi | 21 |
| 2.16 | Team Meeting | 2 hrs | August 15, 2016 8:00 AM | August 15, 2016 10:00 AM | Qiuwen Yao |  |
| 2.17 | Moke up of- ' home(daily)/my profile ' | 3 hrs | August 15, 2016 8:00 AM | August 15, 2016 11:00 AM | Qiuwen Yao |  |
| 2.18 | Moke up of- ' mentor profile ' | 2.5 hrs | August 16, 2016 8:00 AM | August 16, 2016 10:30 AM | Qiuwen Yao |  |
| 2.19 | Study about Ruby online | 6 hrs | August 17, 2016 8:00 AM | August 17, 2016 3:00 PM | Qiuwen Yao | 12 |
| 2.20 | Team Meeting | 2 hrs | August 15, 2016 8:00 AM | August 15, 2016 10:00 AM | Ahmed Fahad Alajmi |  |
| 2.21 | Understand ruby | 4 hrs | August 17, 2016 8:00 AM | August 17, 2016 12:00 PM | Ahmed Fahad Alajmi |  |
| 2.22 | Read about ruby | 2 hrs | August 18, 2016 8:00 AM | August 18, 2016 10:00 AM | Ahmed Fahad Alajmi | 8 |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | Sprint 3 (Week 6) | 6 days | August 19, 2016 8:00 AM | August 26, 2016 5:00 PM |  |  |
| 3.1 | Team Meeting | 3 hrs | August 22, 2016 8:00 AM | August 22, 2016 11:00 AM | Rittidate Kittisarathamma |  |
| 3.2 | Database Schema Design | 5 hrs | August 22, 2016 8:00 AM | August 22, 2016 2:00 PM | Rittidate Kittisarathamma |  |
| 3.3 | Add Component of registration page | 5 hrs | August 23, 2016 8:00 AM | August 23, 2016 2:00 PM | Rittidate Kittisarathamma |  |
| 3.4 | Create route needed and add database | 8 hrs | August 24, 2016 8:00 AM | August 24, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 3.5 | Implement database with registration page | 8 hrs | August 25, 2016 8:00 AM | August 25, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 3.6 | Add Component of setting page | 6 hrs | August 26, 2016 8:00 AM | August 26, 2016 3:00 PM | Rittidate Kittisarathamma | 35 |
| 3.7 | Team Meeting | 3 hrs | August 22, 2016 8:00 AM | August 22, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 3.8 | Design Dashboard Page | 4 hrs | August 22, 2016 8:00 AM | August 22, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 3.9 | Work on registration page design | 6 hrs | August 23, 2016 8:00 AM | August 23, 2016 3:00 PM | Saransh Sandeepbhai Seth |  |
| 3.10 | Changes in dashboard and registration design | 7 hrs | August 24, 2016 8:00 AM | August 24, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |
| 3.11 | Design and Work on registration page | 7 hrs | August 25, 2016 8:00 AM | August 25, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |
| 3.12 | Complete and Enhance registration page | 1 hr | August 26, 2016 8:00 AM | August 26, 2016 9:00 AM | Saransh Sandeepbhai Seth |  |
| 3.13 | Add slider on dashboard and final touchup | 5 hrs | August 26, 2016 8:00 AM | August 26, 2016 2:00 PM | Saransh Sandeepbhai Seth | 33 |
| 3.14 | Team Meeting | 3 hrs | August 22, 2016 8:00 AM | August 22, 2016 11:00 AM | Amandeep Nagi |  |
| 3.15 | Front-end Dashboard design | 4 hrs | August 22, 2016 8:00 AM | August 22, 2016 12:00 PM | Amandeep Nagi |  |
| 3.16 | Learn to work with materialise CSS | 6 hrs | August 23, 2016 8:00 AM | August 23, 2016 3:00 PM | Amandeep Nagi |  |
| 3.17 | Changes in design of dashboard and registration | 7 hrs | August 24, 2016 8:00 AM | August 24, 2016 4:00 PM | Amandeep Nagi |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 3.18 | Work of registration page and learn more features of materialize CSS | 7.5 hrs | August 25, 2016 8:00 AM | August 25, 2016 4:30 PM | Amandeep Nagi |  |
| 3.19 | work to finalize and enhance registration page | 4 hrs | August 26, 2016 8:00 AM | August 26, 2016 12:00 PM | Amandeep Nagi |  |
| 3.20 | Team Meeting | 3 hrs | August 22, 2016 8:00 AM | August 22, 2016 11:00 AM | Qiuwen Yao |  |
| 3.21 | Creating database diagram | 4 hrs | August 23, 2016 8:00 AM | August 23, 2016 12:00 PM | Qiuwen Yao |  |
| 3.22 | Update moke up | 4 hrs | August 23, 2016 8:00 AM | August 23, 2016 12:00 PM | Qiuwen Yao |  |
| 3.23 | Learn using ruby for creating data table | 6.5 hrs | August 24, 2016 8:00 AM | August 24, 2016 3:30 PM | Qiuwen Yao |  |
| 3.24 | try to create data table in ' sublime time ' | 6 hrs | August 25, 2016 8:00 AM | August 25, 2016 3:00 PM | Qiuwen Yao |  |
| 3.25 | Learing about Databases and Migrations | 3 hrs | August 26, 2016 8:00 AM | August 26, 2016 11:00 AM | Qiuwen Yao | 26.5 |
| 3.26 | Team Meeting | 3 hrs | August 22, 2016 8:00 AM | August 22, 2016 11:00 AM | Ahmed Fahad Alajmi |  |
| 3.27 | Design Database Schema | 3 hrs | August 23, 2016 8:00 AM | August 23, 2016 11:00 AM | Ahmed Fahad Alajmi |  |
| 3.28 | Update Database Schema | 3 hrs | August 24, 2016 8:00 AM | August 24, 2016 11:00 AM | Ahmed Fahad Alajmi | 9 |
| 4 | Sprint 4 (Week 7) | 11 days | August 26, 2016 8:00 AM | September 9, 2016 5:00 PM |  |  |
| 4.1 | Team Meeting | 3 hrs | September 5, 2016 8:00 AM | September 5, 2016 11:00 AM | Rittidate Kittisarathamma |  |
| 4.2 | Fix bugs | 4 hrs | September 5, 2016 8:00 AM | September 5, 2016 12:00 PM | Rittidate Kittisarathamma |  |
| 4.3 | Setting page create | 7 hrs | September 6, 2016 8:00 AM | September 6, 2016 4:00 PM | Rittidate Kittisarathamma |  |
| 4.4 | Setting page fields | 6 hrs | September 7, 2016 8:00 AM | September 7, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 4.5 | Setting page (changing password) | 6 hrs | September 8, 2016 8:00 AM | September 8, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 4.6 | Payment page design | 7 hrs | September 9, 2016 8:00 AM | September 9, 2016 4:00 PM | Rittidate Kittisarathamma |  |
| 4.7 | AWS setting up | 4 hrs | September 8, 2016 8:00 AM | September 8, 2016 12:00 PM | Rittidate Kittisarathamma | 37 |
| 4.8 | Team Meeting | 3 hrs | September 5, 2016 8:00 AM | September 5, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 4.9 | Learn HAML syntax and coding | 4 hrs | September 3, 2016 8:00 AM | September 3, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 4.10 | Research for web browser calling | 3 hrs | September 4, 2016 8:00 AM | September 4, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 4.11 | Learn about coffeescript | 4 hrs | September 5, 2016 8:00 AM | September 5, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 4.12 | Setting page design | 5 hrs | September 6, 2016 8:00 AM | September 6, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 4.13 | Fix design errors | 3 hrs | September 7, 2016 8:00 AM | September 7, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 4.14 | Learn HAML syntax and coding | 3 hrs | September 8, 2016 8:00 AM | September 8, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 4.15 | Settings page final design | 2 hrs | September 8, 2016 8:00 AM | September 8, 2016 10:00 AM | Saransh Sandeepbhai Seth |  |
| 4.16 | Payment page design and dashboard beautify | 4 hrs | September 9, 2016 8:00 AM | September 9, 2016 12:00 PM | Saransh Sandeepbhai Seth | 31 |
| 4.17 | Team Meeting | 3 hrs | September 5, 2016 8:00 AM | September 5, 2016 11:00 AM | Amandeep Nagi |  |
| 4.18 | Ruby on rails tutorials | 3.5 hrs | September 5, 2016 8:00 AM | September 5, 2016 11:30 AM | Amandeep Nagi |  |
| 4.19 | Learn about HAML | 6 hrs | September 6, 2016 8:00 AM | September 6, 2016 3:00 PM | Amandeep Nagi |  |
| 4.20 | Learn about the vrious options in materialize | 3 hrs | September 7, 2016 8:00 AM | September 7, 2016 11:00 AM | Amandeep Nagi |  |
| 4.21 | working on dashboard page | 3 hrs | September 7, 2016 8:00 AM | September 7, 2016 11:00 AM | Amandeep Nagi |  |
| 4.22 | practice of ruby on rails with materialize | 5 hrs | September 8, 2016 8:00 AM | September 8, 2016 2:00 PM | Amandeep Nagi |  |
| 4.23 | Design of settings page | 2 hrs | September 8, 2016 8:00 AM | September 8, 2016 10:00 AM | Amandeep Nagi |  |
| 4.24 | Final design for settings  page | 5 hrs | September 9, 2016 8:00 AM | September 9, 2016 2:00 PM | Amandeep Nagi | 30.5 |
| 4.25 | Team Meeting | 3 hrs | September 5, 2016 8:00 AM | September 5, 2016 11:00 AM | Qiuwen Yao |  |
| 4.26 | learn Ruby on rails tutorials | 4 hrs | September 6, 2016 8:00 AM | September 6, 2016 12:00 PM | Qiuwen Yao |  |
| 4.27 | creating files and practice about ruby on rails | 4 hrs | September 6, 2016 8:00 AM | September 6, 2016 12:00 PM | Qiuwen Yao |  |
| 4.28 | learn database and migration tutorials | 6 hrs | September 7, 2016 8:00 AM | September 7, 2016 3:00 PM | Qiuwen Yao |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 4.29 | working on database design | 3 hrs | September 7, 2016 8:00 AM | September 7, 2016 11:00 AM | Qiuwen Yao |  |
| 4.30 | creating database schema on vertabelo | 5 hrs | September 8, 2016 8:00 AM | September 8, 2016 2:00 PM | Qiuwen Yao |  |
| 4.31 | try to work on database coding | 2 hrs | September 8, 2016 8:00 AM | September 8, 2016 10:00 AM | Qiuwen Yao |  |
| 4.32 | database schema changing | 3 hrs | September 9, 2016 8:00 AM | September 9, 2016 11:00 AM | Qiuwen Yao | 30 |
| 4.33 | Team Meeting | 3 hrs | September 5, 2016 8:00 AM | September 5, 2016 11:00 AM | Ahmed Fahad Alajmi |  |
| 4.34 | Review database normelazation | 6 hrs | September 5, 2016 8:00 AM | September 5, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 4.35 | Figure out a message table for the schema | 5 hrs | September 6, 2016 8:00 AM | September 6, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 4.36 | Create database schema in  Dia | 4 hrs | September 6, 2016 8:00 AM | September 6, 2016 12:00 PM | Ahmed Fahad Alajmi |  |
| 4.37 | Update database schema | 3 hrs | September 7, 2016 8:00 AM | September 7, 2016 11:00 AM | Ahmed Fahad Alajmi |  |
| 4.38 | Review database coding | 5 hrs | September 7, 2016 8:00 AM | September 7, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 4.39 | Ruby on rails tutorials | 4 hrs | September 6, 2016 8:00 AM | September 6, 2016 12:00 PM | Ahmed Fahad Alajmi | 30 |
| 5 | Sprint 5 (Week8) | 6 days | September 9, 2016 8:00 AM | September 16, 2016 5:00 PM |  |  |
| 5.1 | Payment page | 8 hrs | September 11, 2016 8:00 AM | September 11, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 5.2 | Category and subcategory database schema | 8 hrs | September 12, 2016 8:00 AM | September 12, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 5.3 | Create category page | 8 hrs | September 13, 2016 8:00 AM | September 13, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 5.4 | Add functions and javascript to category | 8 hrs | September 14, 2016 8:00 AM | September 14, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 5.5 | Add Category to my profile page | 3 hrs | September 15, 2016 8:00 AM | September 15, 2016 11:00 AM | Rittidate Kittisarathamma |  |
| 5.6 | Create new feed database schema | 5 hrs | September 15, 2016 8:00 AM | September 15, 2016 2:00 PM | Rittidate Kittisarathamma |  |
| 5.7 | Finish my profile page | 5 hrs | September 16, 2016 8:00 AM | September 16, 2016 2:00 PM | Rittidate Kittisarathamma | 45 |
| 5.8 | My profile page design | 6 hrs | September 10, 2016 8:00 AM | September 10, 2016 3:00 PM | Saransh Sandeepbhai Seth |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 5.9 | My profile page design | 5 hrs | September 11, 2016 8:00 AM | September 11, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 5.10 | My profile page design | 7 hrs | September 12, 2016 8:00 AM | September 12, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |
| 5.11 | Dashboard feed design | 5 hrs | September 14, 2016 8:00 AM | September 14, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 5.12 | Dashboard feed design | 6 hrs | September 15, 2016 8:00 AM | September 15, 2016 3:00 PM | Saransh Sandeepbhai Seth |  |
| 5.13 | Add share button to dashboard feed | 3 hrs | September 15, 2016 8:00 AM | September 15, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 5.14 | Minor changes and finalizing things | 4 hrs | September 16, 2016 8:00 AM | September 16, 2016 12:00 PM | Saransh Sandeepbhai Seth | 36 |
| 5.15 | My profile page design(Side nav) | 6 hrs | September 10, 2016 8:00 AM | September 10, 2016 3:00 PM | Amandeep Nagi |  |
| 5.16 | My profile page design(Side nav) | 4 hrs | September 11, 2016 8:00 AM | September 11, 2016 12:00 PM | Amandeep Nagi |  |
| 5.17 | My profile page design(Feeds) | 5 hrs | September 12, 2016 8:00 AM | September 12, 2016 2:00 PM | Amandeep Nagi |  |
| 5.18 | Programming for front end | 6 hrs | September 14, 2016 8:00 AM | September 14, 2016 3:00 PM | Amandeep Nagi |  |
| 5.19 | Programming for front end | 6 hrs | September 15, 2016 8:00 AM | September 15, 2016 3:00 PM | Amandeep Nagi |  |
| 5.20 | Final merge | 4 hrs | September 16, 2016 8:00 AM | September 16, 2016 12:00 PM | Amandeep Nagi | 31 |
| 5.21 | Mock up for setting and change password pages | 4 hrs | September 12, 2016 8:00 AM | September 12, 2016 12:00 PM | Qiuwen Yao |  |
| 5.22 | Plan for the technical report < first version > | 4 hrs | September 12, 2016 8:00 AM | September 12, 2016 12:00 PM | Qiuwen Yao |  |
| 5.23 | Mock up for the rest pages | 6 hrs | September 13, 2016 8:00 AM | September 13, 2016 3:00 PM | Qiuwen Yao |  |
| 5.24 | Start with the technical report | 5 hrs | September 14, 2016 8:00 AM | September 14, 2016 2:00 PM | Qiuwen Yao |  |
| 5.25 | Update the mock up pages | 6 hrs | September 15, 2016 8:00 AM | September 15, 2016 3:00 PM | Qiuwen Yao |  |
| 5.26 | Learning database associations on lynda | 2 hrs | September 15, 2016 8:00 AM | September 15, 2016 10:00 AM | Qiuwen Yao |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 5.27 | Change and upload the mock up pages relay on updates | 4 hrs | September 16, 2016 8:00 AM | September 16, 2016 12:00 PM | Qiuwen Yao | 31 |
| 5.28 | Learn databasing in Ruby | 4 hrs | September 11, 2016 8:00 AM | September 11, 2016 12:00 PM | Ahmed Fahad Alajmi |  |
| 5.29 | Search to create database tables in ruby | 7 hrs | September 12, 2016 8:00 AM | September 12, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 5.30 | Create database schema for category, user relation category, and subcategory | 4 hrs | September 13, 2016 8:00 AM | September 13, 2016 12:00 PM | Ahmed Fahad Alajmi |  |
| 5.31 | Update the database schema | 2 hrs | September 13, 2016 8:00 AM | September 13, 2016 10:00 AM | Ahmed Fahad Alajmi |  |
| 5.32 | In ruby, create database tables for category, user relation category, and subcategory | 5 hrs | September 13, 2016 8:00 AM | September 13, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 5.33 | In ruby, create database tables for category, user relation category, and subcategory | 6 hrs | September 14, 2016 8:00 AM | September 14, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 5.34 | Search to create new branch in Ruby | 1 hr | September 14, 2016 8:00 AM | September 14, 2016 9:00 AM | Ahmed Fahad Alajmi | 29 |
| 6 | Sprint 6 (Week9) | 5.63 days | September 16, 2016 8:00 AM | September 23, 2016 2:00 PM |  |  |
| 6.1 | Payment default function | 4 hrs | September 18, 2016 8:00 AM | September 18, 2016 12:00 PM | Rittidate Kittisarathamma |  |
| 6.2 | Category bar on my profile page | 7 hrs | September 19, 2016 8:00 AM | September 19, 2016 4:00 PM | Rittidate Kittisarathamma |  |
| 6.3 | Follow function | 8 hrs | September 20, 2016 8:00 AM | September 20, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 6.4 | Category popup on my profile page | 8 hrs | September 21, 2016 8:00 AM | September 21, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 6.5 | Mentee and Mentor show on my profile | 4 hrs | September 22, 2016 8:00 AM | September 22, 2016 12:00 PM | Rittidate Kittisarathamma |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 6.6 | Courses database schema | 4 hrs | September 22, 2016 8:00 AM | September 22, 2016 12:00 PM | Rittidate Kittisarathamma |  |
| 6.7 | Add Courses on setting page and myprofile | 5 hrs | September 23, 2016 8:00 AM | September 23, 2016 2:00 PM | Rittidate Kittisarathamma | 40 |
| 6.8 | Front end task division | 2 hrs | September 17, 2016 8:00 AM | September 17, 2016 10:00 AM | Saransh Sandeepbhai Seth |  |
| 6.9 | Radio button for payment | 5 hrs | September 18, 2016 8:00 AM | September 18, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 6.10 | Popup on category bar | 5.5 hrs | September 19, 2016 8:00 AM | September 19, 2016 2:30 PM | Saransh Sandeepbhai Seth |  |
| 6.11 | Notification Icon on header | 5 hrs | September 20, 2016 8:00 AM | September 20, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 6.12 | Notification icon add badge class | 5.5 hrs | September 21, 2016 8:00 AM | September 21, 2016 2:30 PM | Saransh Sandeepbhai Seth |  |
| 6.13 | Mentor profile design | 5.5 hrs | September 22, 2016 8:00 AM | September 22, 2016 2:30 PM | Saransh Sandeepbhai Seth |  |
| 6.14 | Mentor profile design | 3.5 hrs | September 23, 2016 8:00 AM | September 23, 2016 11:30 AM | Saransh Sandeepbhai Seth | 32 |
| 6.15 | Front end task division | 2 hrs | September 17, 2016 8:00 AM | September 17, 2016 10:00 AM | Amandeep Nagi |  |
| 6.16 | Pair Programming with Saransh for Radio button for payment | 5 hrs | September 18, 2016 8:00 AM | September 18, 2016 2:00 PM | Amandeep Nagi |  |
| 6.17 | work on design for Popup and search on appropriate  images for slider | 5.5 hrs | September 19, 2016 8:00 AM | September 19, 2016 2:30 PM | Amandeep Nagi |  |
| 6.18 | Pair Programming with Saransh for Notification Icon on header | 5 hrs | September 20, 2016 8:00 AM | September 20, 2016 2:00 PM | Amandeep Nagi |  |
| 6.19 | Pair Programming with Saransh for Notification icon add badge class | 4.5 hrs | September 21, 2016 8:00 AM | September 21, 2016 1:30 PM | Amandeep Nagi |  |
| 6.20 | work on design of Mentor profile and slider quotes | 5.5 hrs | September 22, 2016 8:00 AM | September 22, 2016 2:30 PM | Amandeep Nagi |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 6.21 | Pair Programming with Saransh for Mentor profile  design | 3.5 hrs | September 23, 2016 8:00 AM | September 23, 2016 11:30 AM | Amandeep Nagi | 32 |
| 6.22 | Planning for technical report | 3 hrs | September 18, 2016 8:00 AM | September 18, 2016 11:00 AM | Qiuwen Yao |  |
| 6.23 | Get some sample reports as references for planning | 5 hrs | September 19, 2016 8:00 AM | September 19, 2016 2:00 PM | Qiuwen Yao |  |
| 6.24 | Start with < Executive Summary > part and finish half of it | 2 hrs | September 19, 2016 8:00 AM | September 19, 2016 10:00 AM | Qiuwen Yao |  |
| 6.25 | update the mock up pages | 4 hrs | September 20, 2016 8:00 AM | September 20, 2016 12:00 PM | Qiuwen Yao |  |
| 6.26 | start with < Technical  framework > and finish part of it | 3 hrs | September 20, 2016 8:00 AM | September 20, 2016 11:00 AM | Qiuwen Yao |  |
| 6.27 | keep going on with < Technical framework > | 4 hrs | September 21, 2016 8:00 AM | September 21, 2016 12:00 PM | Qiuwen Yao |  |
| 6.28 | start plan for < Test specifications > | 3 hrs | September 21, 2016 8:00 AM | September 21, 2016 11:00 AM | Qiuwen Yao |  |
| 6.29 | start with the test and organise the sceenshot and data | 6 hrs | September 22, 2016 8:00 AM | September 22, 2016 3:00 PM | Qiuwen Yao |  |
| 6.30 | update the mock up pages | 3 hrs | September 23, 2016 8:00 AM | September 23, 2016 11:00 AM | Qiuwen Yao | 33 |
| 6.31 | Configure cloud9 database | 5 hrs | September 18, 2016 8:00 AM | September 18, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 6.32 | Configure cloude9 database | 7 hrs | September 19, 2016 8:00 AM | September 19, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 6.33 | Search online for such followers data base attribuates | 3 hrs | September 20, 2016 8:00 AM | September 20, 2016 11:00 AM | Ahmed Fahad Alajmi |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 6.34 | Configure cloud9 database | 6 hrs | September 21, 2016 8:00 AM | September 21, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 6.35 | Design followers database schema | 2 hrs | September 21, 2016 8:00 AM | September 21, 2016 10:00 AM | Ahmed Fahad Alajmi |  |
| 6.36 | Implement and migrate  followers table in the schema file | 6 hrs | September 22, 2016 8:00 AM | September 22, 2016 3:00 PM | Ahmed Fahad Alajmi | 29 |
| 7 | Sprint 7 (Week10) | 7 days | September 23, 2016 8:00 AM | October 3, 2016 5:00 PM |  |  |
| 7.1 | Course and price function | 8 hrs | September 26, 2016 8:00 AM | September 26, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 7.2 | Prepare page and route for course function | 8 hrs | September 27, 2016 8:00 AM | September 27, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 7.3 | Fix heroku server and move server | 10 hrs | September 28, 2016 8:00 AM | September 29, 2016 10:00 AM | Rittidate Kittisarathamma |  |
| 7.4 | Facebook login fix | 4 hrs | September 29, 2016 8:00 AM | September 29, 2016 12:00 PM | Rittidate Kittisarathamma |  |
| 7.5 | Rating function | 8 hrs | September 30, 2016 8:00 AM | September 30, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 7.6 | Arrangment applying course page | 8 hrs | October 1, 2016 8:00 AM | October 1, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 7.7 | Fix bugs and merge master | 5 hrs | October 2, 2016 8:00 AM | October 2, 2016 2:00 PM | Rittidate Kittisarathamma | 51 |
| 7.8 | Front end task division and planning | 3 hrs | September 24, 2016 8:00 AM | September 24, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 7.9 | Page for contact button | 5 hrs | September 25, 2016 8:00 AM | September 25, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 7.10 | Page for payment(mentee) | 7 hrs | September 26, 2016 8:00 AM | September 26, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |
| 7.11 | Message Icon on header add badge class | 3 hrs | September 27, 2016 8:00 AM | September 27, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 7.12 | Add page transitions | 5 hrs | September 28, 2016 8:00 AM | September 28, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 7.13 | Add hover tooltips for areas section in profile | 3 hrs | September 29, 2016 8:00 AM | September 29, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 7.14 | Add grey default text for mentor profile | 2 hrs | September 30, 2016 8:00 AM | September 30, 2016 10:00 AM | Saransh Sandeepbhai Seth |  |
| 7.15 | Design notification page | 7 hrs | October 1, 2016 8:00 AM | October 1, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 7.16 | Design wait page | 6 hrs | October 2, 2016 8:00 AM | October 2, 2016 3:00 PM | Saransh Sandeepbhai Seth | 41 |
| 7.17 | Front end task division and planning | 3 hrs | September 24, 2016 8:00 AM | September 24, 2016 11:00 AM | Amandeep Nagi |  |
| 7.18 | Design of page for contact | 6 hrs | September 25, 2016 8:00 AM | September 25, 2016 3:00 PM | Amandeep Nagi |  |
| 7.19 | Front-end design for payment for mentee | 5 hrs | September 26, 2016 8:00 AM | September 26, 2016 2:00 PM | Amandeep Nagi |  |
| 7.20 | Design of page for payment | 5 hrs | September 27, 2016 8:00 AM | September 27, 2016 2:00 PM | Amandeep Nagi |  |
| 7.21 | work on adding hover on areas section of profile | 3 hrs | September 29, 2016 8:00 AM | September 29, 2016 11:00 AM | Amandeep Nagi |  |
| 7.22 | Default text for mentor profile | 2 hrs | September 30, 2016 8:00 AM | September 30, 2016 10:00 AM | Amandeep Nagi |  |
| 7.23 | Design of the wait page | 5 hrs | October 1, 2016 8:00 AM | October 1, 2016 2:00 PM | Amandeep Nagi |  |
| 7.24 | Front-end design of notification page | 6 hrs | October 2, 2016 8:00 AM | October 2, 2016 3:00 PM | Amandeep Nagi | 35 |
| 7.25 | Create the technical documentation new version planning | 3 hrs | September 25, 2016 8:00 AM | September 25, 2016 11:00 AM | Qiuwen Yao |  |
| 7.26 | start with describe the archicture of the system | 4 hrs | September 26, 2016 8:00 AM | September 26, 2016 12:00 PM | Qiuwen Yao |  |
| 7.27 | update for new mock up pages | 3 hrs | September 26, 2016 8:00 AM | September 26, 2016 11:00 AM | Qiuwen Yao |  |
| 7.28 | Update the framework part in document | 6 hrs | September 27, 2016 8:00 AM | September 27, 2016 3:00 PM | Qiuwen Yao |  |
| 7.29 | start with the  implementation and do the screetshot | 5 hrs | September 28, 2016 8:00 AM | September 28, 2016 2:00 PM | Qiuwen Yao |  |
| 7.30 | mock up updates | 3 hrs | September 28, 2016 8:00 AM | September 28, 2016 11:00 AM | Qiuwen Yao |  |
| 7.31 | keep going with the implementation | 4 hrs | September 29, 2016 8:00 AM | September 29, 2016 12:00 PM | Qiuwen Yao |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 7.32 | doing the tests with the existing functions | 4 hrs | September 29, 2016 8:00 AM | September 29, 2016 12:00 PM | Qiuwen Yao |  |
| 7.33 | keep going with the tests | 2 hrs | September 30, 2016 8:00 AM | September 30, 2016 10:00 AM | Qiuwen Yao | 34 |
| 7.34 | Design rating table schema | 5 hrs | September 26, 2016 8:00 AM | September 26, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 7.35 | Implementing rating table | 6 hrs | September 27, 2016 8:00 AM | September 27, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 7.36 | Keep going with implementing rating table | 7 hrs | September 28, 2016 8:00 AM | September 28, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 7.37 | Document menti functional requirment | 6 hrs | September 29, 2016 8:00 AM | September 29, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 7.38 | Document menti nonfunctional requirement | 7 hrs | September 30, 2016 8:00 AM | September 30, 2016 4:00 PM | Ahmed Fahad Alajmi | 29 |
| 8 | Sprint8 (Week11) | 5 days | October 3, 2016 8:00 AM | October 7, 2016 5:00 PM |  |  |
| 8.1 | Message database design | 8 hrs | October 3, 2016 8:00 AM | October 3, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 8.2 | Message page create | 8 hrs | October 4, 2016 8:00 AM | October 4, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 8.3 | Notification and message | 8 hrs | October 5, 2016 8:00 AM | October 5, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 8.4 | Auto send message and notify | 8 hrs | October 6, 2016 8:00 AM | October 6, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 8.5 | task division and planning for front-end | 3 hrs | October 3, 2016 8:00 AM | October 3, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 8.6 | adding hover for header icons | 6 hrs | October 4, 2016 8:00 AM | October 4, 2016 3:00 PM | Saransh Sandeepbhai Seth |  |
| 8.7 | design for message page UI | 4 hrs | October 5, 2016 8:00 AM | October 5, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 8.8 | design for normal message page | 5 hrs | October 5, 2016 8:00 AM | October 5, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 8.9 | searching and testing for relevant chat style | 3 hrs | October 6, 2016 8:00 AM | October 6, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 8.10 | design for chat page | 5 hrs | October 6, 2016 8:00 AM | October 6, 2016 2:00 PM | Saransh Sandeepbhai Seth |  |
| 8.11 | Pair programming with Amandeep for adding time on notification card | 2.5 hrs | October 7, 2016 8:00 AM | October 7, 2016 10:30 AM | Saransh Sandeepbhai Seth |  |
| 8.12 | Pair programming for adding time on message card | 2.5 hrs | October 7, 2016 8:00 AM | October 7, 2016 10:30 AM | Saransh Sandeepbhai Seth | 31 |
| 8.13 | Task division and planning meeting | 3 hrs | October 3, 2016 8:00 AM | October 3, 2016 11:00 AM | Amandeep Nagi |  |
| 8.14 | Design for message UI | 6 hrs | October 4, 2016 8:00 AM | October 4, 2016 3:00 PM | Amandeep Nagi |  |
| 8.15 | searching of various styles for messaging page | 3 hrs | October 5, 2016 8:00 AM | October 5, 2016 11:00 AM | Amandeep Nagi |  |
| 8.16 | searching and testing of various styles for chatting | 5 hrs | October 5, 2016 8:00 AM | October 5, 2016 2:00 PM | Amandeep Nagi |  |
| 8.17 | Design of message page | 5 hrs | October 6, 2016 8:00 AM | October 6, 2016 2:00 PM | Amandeep Nagi |  |
| 8.18 | Design of chat page | 3 hrs | October 6, 2016 8:00 AM | October 6, 2016 11:00 AM | Amandeep Nagi |  |
| 8.19 | looking into materialize for further styling | 1 hr | October 7, 2016 8:00 AM | October 7, 2016 9:00 AM | Amandeep Nagi |  |
| 8.20 | Pair programming with Saransh for Time on the notification and message cards | 4 hrs | October 7, 2016 8:00 AM | October 7, 2016 12:00 PM | Amandeep Nagi | 30 |
| 8.21 | mock up pages update | 3 hrs | October 3, 2016 8:00 AM | October 3, 2016 11:00 AM | Qiuwen Yao |  |
| 8.22 | mock up pages update continue | 4 hrs | October 4, 2016 8:00 AM | October 4, 2016 12:00 PM | Qiuwen Yao |  |
| 8.23 | archicture-- website flow image create | 3 hrs | October 4, 2016 8:00 AM | October 4, 2016 11:00 AM | Qiuwen Yao |  |
| 8.24 | checking functional requirements | 3 hrs | October 5, 2016 8:00 AM | October 5, 2016 11:00 AM | Qiuwen Yao |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 8.25 | prepare for test case relay on functional requirements | 4 hrs | October 5, 2016 8:00 AM | October 5, 2016 12:00 PM | Qiuwen Yao |  |
| 8.26 | checking non-functional requirements | 2 hrs | October 5, 2016 8:00 AM | October 5, 2016 10:00 AM | Qiuwen Yao |  |
| 8.27 | start with test cases | 6 hrs | October 6, 2016 8:00 AM | October 6, 2016 3:00 PM | Qiuwen Yao |  |
| 8.28 | archicture-- database schema creating | 5 hrs | October 7, 2016 8:00 AM | October 7, 2016 2:00 PM | Qiuwen Yao | 30 |
| 8.29 | Design database schema for message and conversation tables | 5 hrs | October 2, 2016 8:00 AM | October 2, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 8.30 | Implement message and conversation tables | 7 hrs | October 3, 2016 8:00 AM | October 3, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 8.31 | Keep going with the tables | 7 hrs | October 4, 2016 8:00 AM | October 4, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 8.32 | Document requirements (functional and non functional requirements) | 6 hrs | October 5, 2016 8:00 AM | October 5, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 8.33 | Document requirements (functional and non functional requirements) | 6 hrs | October 6, 2016 8:00 AM | October 6, 2016 3:00 PM | Ahmed Fahad Alajmi | 31 |
| 9 | Sprint 9(Week12) | 6 days | October 7, 2016 8:00 AM | October 14, 2016 5:00 PM |  |  |
| 9.1 | Search algorithm | 8 hrs | October 10, 2016 8:00 AM | October 10, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 9.2 | Add more detail on search box | 7 hrs | October 11, 2016 8:00 AM | October 11, 2016 4:00 PM | Rittidate Kittisarathamma |  |
| 9.3 | Fix feed message | 8 hrs | October 12, 2016 8:00 AM | October 12, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 9.4 | implement menter ' s area new design | 8 hrs | October 13, 2016 8:00 AM | October 13, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 9.5 | Add mentor ' s area icon on search and profile | 4 hrs | October 14, 2016 8:00 AM | October 14, 2016 12:00 PM | Rittidate Kittisarathamma | 35 |
| 9.6 | Task division | 3 hrs | October 10, 2016 8:00 AM | October 10, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 9.7 | initial search design | 8 hrs | October 11, 2016 8:00 AM | October 11, 2016 5:00 PM | Saransh Sandeepbhai Seth |  |
| 9.8 | add transitions to search design | 7 hrs | October 12, 2016 8:00 AM | October 12, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |
| 9.9 | search list design | 7 hrs | October 13, 2016 8:00 AM | October 13, 2016 4:00 PM | Saransh Sandeepbhai Seth |  |
| 9.10 | add areas drop-down in mentor settings | 4 hrs | October 14, 2016 8:00 AM | October 14, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 9.11 | add new icons in mentor profile | 2.5 hrs | October 14, 2016 8:00 AM | October 14, 2016 10:30 AM | Saransh Sandeepbhai Seth | 31.5 |
| 9.12 | Task division | 3 hrs | October 10, 2016 8:00 AM | October 10, 2016 11:00 AM | Amandeep Nagi |  |
| 9.13 | pair programming with  saransh for initial search design | 8 hrs | October 11, 2016 8:00 AM | October 11, 2016 5:00 PM | Amandeep Nagi |  |
| 9.14 | pair programming with saransh to add transitions on search | 7 hrs | October 12, 2016 8:00 AM | October 12, 2016 4:00 PM | Amandeep Nagi |  |
| 9.15 | pair programming with saransh fro the design of  search list | 7 hrs | October 13, 2016 8:00 AM | October 13, 2016 4:00 PM | Amandeep Nagi |  |
| 9.16 | adding drop-down for areas in mentor settings | 3 hrs | October 14, 2016 8:00 AM | October 14, 2016 11:00 AM | Amandeep Nagi |  |
| 9.17 | add new icons in mentor profile | 3 hrs | October 14, 2016 8:00 AM | October 14, 2016 11:00 AM | Amandeep Nagi | 31 |
| 9.18 | mock up updates(1) | 6 hrs | October 10, 2016 8:00 AM | October 10, 2016 3:00 PM | Qiuwen Yao |  |
| 9.19 | updates database schema of system archicture | 5 hrs | October 11, 2016 8:00 AM | October 11, 2016 2:00 PM | Qiuwen Yao |  |
| 9.20 | mock up updates(2) | 2 hrs | October 11, 2016 8:00 AM | October 11, 2016 10:00 AM | Qiuwen Yao |  |
| 9.21 | started with test cases | 4 hrs | October 12, 2016 8:00 AM | October 12, 2016 12:00 PM | Qiuwen Yao |  |
| 9.22 | started with  implementation of technical report | 5 hrs | October 12, 2016 8:00 AM | October 12, 2016 2:00 PM | Qiuwen Yao |  |
| 9.23 | keep going on with test cases | 6 hrs | October 13, 2016 8:00 AM | October 13, 2016 3:00 PM | Qiuwen Yao |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 9.24 | start with functional requirements and search for templates | 0 hrs | October 14, 2016 5:00 PM | October 14, 2016 5:00 PM | Qiuwen Yao | 31 |
| 9.25 | Requirement specification | 5 hrs | October 9, 2016 8:00 AM | October 9, 2016 2:00 PM | Ahmed Fahad Alajmi |  |
| 9.26 | Requirement specification | 7 hrs | October 10, 2016 8:00 AM | October 10, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 9.27 | Requirement specification | 6 hrs | October 11, 2016 8:00 AM | October 11, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 9.28 | Requirement specification | 7 hrs | October 12, 2016 8:00 AM | October 12, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 9.29 | Requirement specification | 4 hrs | October 13, 2016 8:00 AM | October 13, 2016 12:00 PM | Ahmed Fahad Alajmi | 29 |
| 10 | Sprint 10 (Week13) | 6 days | October 14, 2016 8:00 AM | October 21, 2016 5:00 PM |  |  |
| 10.1 | Resource database schema create | 8 hrs | October 17, 2016 8:00 AM | October 17, 2016 5:00 PM | Rittidate Kittisarathamma |  |
| 10.2 | Validate resource type | 6 hrs | October 18, 2016 8:00 AM | October 18, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 10.3 | Upload photo on feed message and message | 6 hrs | October 19, 2016 8:00 AM | October 19, 2016 3:00 PM | Rittidate Kittisarathamma |  |
| 10.4 | Share content from other ' s feed message | 7 hrs | October 20, 2016 8:00 AM | October 20, 2016 4:00 PM | Rittidate Kittisarathamma |  |
| 10.5 | Delete chatting history | 5 hrs | October 21, 2016 8:00 AM | October 21, 2016 2:00 PM | Rittidate Kittisarathamma | 32 |
| 10.6 | meeting and task division | 3 hrs | October 17, 2016 8:00 AM | October 17, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 10.7 | basic design of resource page(official resources) | 4 hrs | October 18, 2016 8:00 AM | October 18, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 10.8 | basic design of resource page(user resources) | 4 hrs | October 18, 2016 8:00 AM | October 18, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 10.9 | add search bar in resource page | 4 hrs | October 19, 2016 8:00 AM | October 19, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 10.10 | upload resource button | 3 hrs | October 19, 2016 8:00 AM | October 19, 2016 11:00 AM | Saransh Sandeepbhai Seth |  |
| 10.11 | testing site fucntionality | 4 hrs | October 20, 2016 8:00 AM | October 20, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 10.12 | fixing of bugs found while testing | 4 hrs | October 20, 2016 8:00 AM | October 20, 2016 12:00 PM | Saransh Sandeepbhai Seth |  |
| 10.13 | review documentation | 5 hrs | October 21, 2016 8:00 AM | October 21, 2016 2:00 PM | Saransh Sandeepbhai Seth | 31 |
| 10.14 | meeting and task division | 3 hrs | October 17, 2016 8:00 AM | October 17, 2016 11:00 AM | Amandeep Nagi |  |
| 10.15 | design of resource page for official and user resources | 8 hrs | October 18, 2016 8:00 AM | October 18, 2016 5:00 PM | Amandeep Nagi |  |
| 10.16 | pair progamming with saransh for search bar in resource page | 4 hrs | October 19, 2016 8:00 AM | October 19, 2016 12:00 PM | Amandeep Nagi |  |
| 10.17 | pair programming for upload resouce button | 3 hrs | October 19, 2016 8:00 AM | October 19, 2016 11:00 AM | Amandeep Nagi |  |
| 10.18 | testing of site functionality | 3 hrs | October 20, 2016 8:00 AM | October 20, 2016 11:00 AM | Amandeep Nagi |  |
| 10.19 | technical report work( requirements review and editing) | 5 hrs | October 20, 2016 8:00 AM | October 20, 2016 2:00 PM | Amandeep Nagi |  |
| 10.20 | fix bugs found after testing | 6 hrs | October 21, 2016 8:00 AM | October 21, 2016 3:00 PM | Amandeep Nagi | 32 |
| 10.21 | Start adding functional requirements | 3 hrs | October 17, 2016 8:00 AM | October 17, 2016 11:00 AM | Qiuwen Yao |  |
| 10.22 | Finish Functional requirements specification first version | 6 hrs | October 18, 2016 8:00 AM | October 18, 2016 3:00 PM | Qiuwen Yao |  |
| 10.23 | Start doing several test cases relay on FRs | 5 hrs | October 19, 2016 8:00 AM | October 19, 2016 2:00 PM | Qiuwen Yao |  |
| 10.24 | Editing technical report and organise | 3 hrs | October 19, 2016 8:00 AM | October 19, 2016 11:00 AM | Qiuwen Yao |  |
| 10.25 | Changing system archicture graph and database schema | 4 hrs | October 20, 2016 8:00 AM | October 20, 2016 12:00 PM | Qiuwen Yao |  |
| 10.26 | Update and rewrite FRs | 5 hrs | October 20, 2016 8:00 AM | October 20, 2016 2:00 PM | Qiuwen Yao |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 10.27 | Adding test cases and record results | 5 hrs | October 21, 2016 8:00 AM | October 21, 2016 2:00 PM | Qiuwen Yao | 31 |
| 10.28 | Requirement specification | 6 hrs | October 16, 2016 8:00 AM | October 16, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 10.29 | Requirement specification | 8 hrs | October 17, 2016 8:00 AM | October 17, 2016 5:00 PM | Ahmed Fahad Alajmi |  |
| 10.30 | Finish Requirement specification | 7 hrs | October 18, 2016 8:00 AM | October 18, 2016 4:00 PM | Ahmed Fahad Alajmi |  |
| 10.31 | Finish Requirement specification | 6 hrs | October 19, 2016 8:00 AM | October 19, 2016 3:00 PM | Ahmed Fahad Alajmi |  |
| 10.32 | Finish Requirement specification | 3 hrs | October 20, 2016 8:00 AM | October 20, 2016 11:00 AM | Ahmed Fahad Alajmi | 30 |

# Project Management tools

Describe what project management tools you used within the project.

# Project Workflow

Describe here the project workflow spring by sprint.

You might use trello/jira screenshots to illustrate the sprints, as well as generate reports from trello/jira.

If your design significantly evolved over sprints, add the description of the design process.

If the requirements were changed from sprint to sprint, add corresponding description here.